## Change
Change history
# | Creator | Version | Date | Change contents
1 | Nguyen Hoang Viet | 1 | 2024-06-26 | Create new estimation
2 | Nguyen Hoang Viet | 2 | 2024-06-28 | Re-assign tasks
3
4
5
6
7

## Estimation
PROJECT PROGRESS ESTIMATION
Fucntion Information |  |  |  |  | Option-1 Est (MD) | Plan |  | Actual |  | Status | Note
No | Category | Person In Charge | Role | To Do List |  | Start date | End date | Start date | End date
1 | Nghiên cứu yêu cầu bài toán (Requirement) | GROUP XX |  |  | 1 |  |  |  |  | 100%
|  | VietNH |  | Tìm hiểu project subject ProjectRequirement.pdf | 1 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 100%
|  | VietNH |  | Tìm nguồn data tiềm năng cho bài tập, chuẩn bị file latex | 1 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 100%
2 | Giải quyết bài toán | GROUP XX |  |  | 3 |  |  |  |  | 100%
|  | YCN |  | Bài 1,2 | 3 | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-07-01 | 100%
|  | NhutNQ |  | Bài 2,3 | 3 | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-07-01 | 100%
|  | VietTXB |  | Bài 3,4 | 3 | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-07-01 | 100%
|  | VietNH |  | Bài 4,5 | 3 | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-07-01 | 100%
|  | DatNM |  | Bài 5,6 | 3 | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-07-01 | 100%
3 | Kiểm tra đầu ra, đánh giá chung | GROUP XX |  |  | 3 |  |  |  |  | 100%
|  | YCN |  | Tính toán lại (bằng tay) sự chính xác của output các bài toán. | 2 | 2024-07-02 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 100%
|  | DatNM | [7 empty] | 100%
|  | NhutNQ |  | Merge lại và điều chỉnh phần giao diện | 1 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 100%
|  | VietTXB | [7 empty] | 100%
4 | Kiểm tra | GROUP 6 |  | Làm slide trên canva và xuất ra file MAS291_PROJECT_GROUP_XX.PPTX | 1 |  |  |  |  | 100%
|  | VietNH |  | Họp và thuyết trình thử | 1 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 2024-07-14 | 100%
0
Total Man Days |  |  |  |  | 6 | [5 empty] | MD
[5 empty] | 0.3 | [5 empty] | MM
[5 empty] | 0.33 | [5 empty] | MM + 10% (PM)